## 30.10.25
UNEW-EthosEnergy // NSRP's Fuel Nozzle Repair Schedule
Part Details |  |  |  |  | Repair Process - Estimated Dates | [5 empty] | Post-Repair Activities - Estimated Dates
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments | Final Assembly | Final Flow Test & Calibration | Finishing Operations | Job Complete | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | Liner Pin | In Stock | N/A - New parts to be fitted during final assembly |  |  |  | Parts ready to fit when required | 2026-01-25 | 2026-01-31 | 2026-03-01 | 2025-03-06 | Delay to finishing operations due to E-Seal lead time - See Row 18
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | Liquid Cartridge Assembly | 2025-11-30 | N/A | 2025-12-01 | 2025-12-11 | 2025-12-15
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | Liquid Cartridge Tip | 2025-11-30 | In Progress | 2025-12-01 | 2025-12-11 | 2025-12-15 | Machining commenced early
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | Water Cartridge Tip | In Stock | In Stock | 2025-11-15 | 2025-11-22 | 2025-11-26 | Stocked parts, Repair work to commence when possible in workshop production schedule
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | End Cover Gas Swirlers | 2025-12-28 | In Progress | 2025-12-29 | 2026-01-18 | 2026-01-25 | Machining commenced early
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Material Arrival Date | Forming | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | EthosEnergy Thailand Nghi Son Refinery | 77062 | Water Pipes | In Stock | 2025-11-03 | N/A | 2025-11-13 | 2025-11-20 | Material on-site - Forming of pipes to commence
Part Details
| Cust. Name | Part Description | Parts Arrival Date
1 |  | End Cover Steam Plate E-Seal | 2026-03-01
2 |  | Steam Inlet Blank Seal | 31-Nov-25
3 |  | Liquid Cart. Crush Seals | In Stock
4 |  | Water Cart. Spiral Wound Gasket | 31-Nov-25
5 |  | Fuel Distribution Valve O-Ring Seal A | In Stock
6 |  | Fuel Distribution Valve O-Ring Seal B | In Stock
7 |  | Water Cartridge Tip | In Stock
8 |  | Fuel Distribution Valve Spring Seal | In Stock
Formulas:
Final Flow Test & Calibration = [Post-Repair Activities - Estimated Dates]+6
Welding = [Repair Process - Estimated Dates]+1

## Photo 30.10.25
UNEW-EthosEnergy // NSRP's Fuel Nozzle Repair Schedule
Part Details |  |  |  |  | Photographs
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liner Pin | #VALUE! | [5 empty] | Parts In Stock, Ready to Fit
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Assembly | #VALUE! | [5 empty] | Awaiting Parts
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Tip | #VALUE! | [5 empty] | Awaiting Parts - Machining to remove exisiting tips to commence
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Cartridge Tip | [6 empty] | Repair to commence
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | End Cover Gas Swirlers | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | Cracked swirlers being machined out of end cover.
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 |  | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Pipes | #VALUE! | [5 empty] | Material Arrived

## 20.10.25
UNEW-EthosEnergy // NSRP's Fuel Nozzle Repair Schedule
Part Details |  |  |  |  | Repair Process - Estimated Dates | [5 empty] | Post-Repair Activities - Estimated Dates
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments | Final Assembly | Final Flow Test & Calibration | Finishing Operations | Job Complete | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liner Pin | In Stock | N/A - New parts to be fitted during final assembly |  |  |  |  | 2026-01-25 | 2026-01-31 | 2026-03-01 | 2025-03-06 | Delay to finishing operations due to E-Seal lead time - See Row 18
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Assembly | 2025-11-30 | N/A | 2025-12-01 | 2025-12-11 | 2025-12-15
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Tip | 2025-11-30 | 2025-11-01 | 2025-12-01 | 2025-12-11 | 2025-12-15 | Machining to commence prior to arrival of spare parts
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Cartridge Tip | In Stock | In Stock | 2025-11-15 | 2025-11-22 | 2025-11-26 | Stocked parts, Repair work to commence when possible in workshop production schedule
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Parts Arrival Date | Machining | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | End Cover Gas Swirlers | 2025-12-28 | 2025-11-01 | 2025-12-29 | 2026-01-18 | 2026-01-25 | Machining to commence prior to arrival of spare parts
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Material Arrival Date | Forming | Welding | Repair Verifiation (Flow, FPI Pressure Test, Etc.) | Repair Completion Date | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Pipes | 2025-11-02 | 2025-11-03 | N/A | 2025-11-13 | 2025-11-20
Part Details
| Cust. Name | Part Description | Parts Arrival Date
1 |  | End Cover Steam Plate E-Seal | 2026-03-01
2 |  | Steam Inlet Blank Seal | 31-Nov-25
3 |  | Liquid Cart. Crush Seals | In Stock
4 |  | Water Cart. Spiral Wound Gasket | 31-Nov-25
5 |  | Fuel Distribution Valve O-Ring Seal A | In Stock
6 |  | Fuel Distribution Valve O-Ring Seal B | In Stock
7 |  | Water Cartridge Tip | In Stock
8 |  | Fuel Distribution Valve Spring Seal | In Stock
Formulas:
Final Flow Test & Calibration = [Post-Repair Activities - Estimated Dates]+6
Welding = [Repair Process - Estimated Dates]+1

## Photo 20.10.25
UNEW-EthosEnergy // NSRP's Fuel Nozzle Repair Schedule
Part Details |  |  |  |  | Photographs
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liner Pin | #VALUE! | [5 empty] | Photos to be added
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Assembly | #VALUE! | [5 empty] | Awaiting Parts
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Liquid Cartridge Tip | [6 empty] | Awaiting Parts - Machining to remove exisiting tips to commence
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Cartridge Tip | [6 empty] | Repair to commence
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | End Cover Gas Swirlers | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Parts awaiting repair commencement - Cracked swirlers to be machined out of end cover.
EE A&C Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Photo 1 | Photo 2 | Photo 3 | Photo 4 | Photo 5 | Photo 6 | Comments
AB9015557 | UNEW, Inc | Nghi Son Refinery | 77062 | Water Pipes | [6 empty] | Awaiting material