## 08.08.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date | Status
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-07-16 | 2025-07-30 | 2025-08-15 | TBA | TBA | TBA | 2025-10-25 | Incoming Inspection Done > gathering data for incoming inspection report
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-07-15 | 2025-07-17 | 2025-08-15 | TBA | TBA | TBA | 2025-09-27 | FPI in progress next : visual inspection & mapping to report defect
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-07-14 | 2025-08-08 | TBA | TBA | TBA | 2025-08-27 | FPI in progress next : visual inspection & mapping to report defect
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-25 | 2025-09-25 | 2025-10-15 | 2025-10-22 | 2025-10-25 | waiting released the parts to repair process / in queue of Sep
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | 2025-09-01 | 2025-09-18 | 2025-09-25 | 2025-09-27 | waiting released the parts to repair process / in queue of Sep
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-24 | 2025-09-28 | 2025-10-10 | 2025-10-20 | 2025-10-25 | waiting released the parts to repair process / in queue of Sep
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-08-01 | 2025-08-18 | 2025-08-24 | 2025-08-27 | in process : Grit Blast, Machine to correct Dimension, waiting assembly
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-15 | 2025-10-10 | 2025-10-20 | 2025-10-25 | in process : weld & blend repair
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-18 | 2025-10-10 | 2025-10-20 | 2025-10-25 | in process : scallop & weld repair

## Photo 08.08.25
EETH WO# | Part description | Status | Photo1 | Photo2
824025 | MS6001FA STAGE 1 BLADE | Incoming Inspection Done > gathering data for incoming inspection report
824026 | MS6001FA STAGE 2 BLADE | FPI in progress next : visual inspection & mapping to report defect
824027 | MS6001FA STAGE 3 BLADE | FPI in progress next : visual inspection & mapping to report defect
824028 | MS6001FA STAGE 1 NOZZLE | waiting released the parts to repair process / in queue of Sep
824029 | MS6001FA STAGE 2 NOZZLE | waiting released the parts to repair process / in queue of Sep
824030 | MS6001FA STAGE 3 NOZZLE | waiting released the parts to repair process / in queue of Sep
824031 | MS6001FA STAGE 1 SHROUD BLOCK | in process : Grit Blast, Machine to correct Dimension, waiting assembly
824032 | MS6001FA STAGE 2 SHROUD BLOCK | in process : weld & blend repair
824033 | MS6001FA STAGE 3 SHROUD BLOCK | in process : scallop & weld repair

## 01.08.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date | Status
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-07-16 | 2025-07-30 | 2025-08-15 | TBA | TBA | TBA | 2025-10-25 | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-07-15 | 2025-07-17 | 2025-08-15 | TBA | TBA | TBA | 2025-09-27 | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect, cooling hole check, dimension inspection
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-07-14 | 2025-08-08 | TBA | TBA | TBA | 2025-08-27 | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-25 | 2025-09-25 | 2025-10-15 | 2025-10-22 | 2025-10-25 | waiting released the parts to repair process / in queue of Aug
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | 2025-09-01 | 2025-09-18 | 2025-09-25 | 2025-09-27 | waiting released the parts to repair process / in queue of Aug
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-24 | 2025-09-28 | 2025-10-10 | 2025-10-20 | 2025-10-25 | waiting released the parts to repair process / in queue of Aug
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-08-01 | 2025-08-18 | 2025-08-24 | 2025-08-27 | in process : weld repair / blend to remove corrosion / defect
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-15 | 2025-10-10 | 2025-10-20 | 2025-10-25 | in process : machine to remove honetcomb
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-18 | 2025-10-10 | 2025-10-20 | 2025-10-25 | in process : machine to remove honetcomb

## Photo 01.08.25
EETH WO# | Part description | Status | Photo1 | Photo2
824025 | MS6001FA STAGE 1 BLADE | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect
824026 | MS6001FA STAGE 2 BLADE | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect, cooling hole check, dimension inspection
824027 | MS6001FA STAGE 3 BLADE | performed wall thickness inspection & performed CMM dimension next : FPI, visual inspection, record defect
824028 | MS6001FA STAGE 1 NOZZLE | waiting released the parts to repair process / in queue of Aug
824029 | MS6001FA STAGE 2 NOZZLE | waiting released the parts to repair process / in queue of Aug
824030 | MS6001FA STAGE 3 NOZZLE | waiting released the parts to repair process / in queue of Aug
824031 | MS6001FA STAGE 1 SHROUD BLOCK | in process : weld repair / blend to remove corrosion/defect
824032 | MS6001FA STAGE 2 SHROUD BLOCK | in process : machine to remove honetcomb
824033 | MS6001FA STAGE 3 SHROUD BLOCK | in process : machine to remove honetcomb

## 25.7.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date | Status
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-07-16 | 2025-07-30 | 2025-08-15 | TBA | TBA | TBA | 2025-10-25 | performed blending to remove remain coating / next process : Perform heat tint operation to ensure full coating removal
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-07-15 | 2025-07-17 | 2025-08-15 | TBA | TBA | TBA | 2025-09-27 | Performed wall thickness inspection / next : FPI
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-07-14 | 2025-08-08 | TBA | TBA | TBA | 2025-08-27 | Performed wall thickness inspection / next : FPI
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25 | IIR received - released to repair process / in queue
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | TBA | TBA | TBA | 2025-09-27 | IIR received - released to repair process / in queue
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-24 | 2025-09-15 | 2025-10-06 | 2025-10-20 | 2025-10-25 | IIR received - released to repair process / in queue
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-27 | IIR received - released to repair process / in queue
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-22 | 2025-10-06 | 2025-10-20 | 2025-10-25 | IIR received - released to repair process / in queue
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-24 | 2025-09-22 | 2025-10-06 | 2025-10-20 | 2025-10-25 | IIR received - released to repair process / in queue
Definition
IIR | Incoming Inspection Report

## Photo 25.7.25
EETH WO# | Part description | Status | Photo1 | Photo2
824025 | MS6001FA STAGE 1 BLADE | performed blending to remove remain coating next process : Perform heat tint operation to ensure full coating removal
824026 | MS6001FA STAGE 2 BLADE | Performed wall thickness inspection next process : FPI
824027 | MS6001FA STAGE 3 BLADE | Performed wall thickness inspection next process : FPI
824028 | MS6001FA STAGE 1 NOZZLE | IIR received - released to repair process / in queue
824029 | MS6001FA STAGE 2 NOZZLE | IIR received - released to repair process / in queue
824030 | MS6001FA STAGE 3 NOZZLE | IIR received - released to repair process / in queue
824031 | MS6001FA STAGE 1 SHROUD BLOCK | IIR received - released to repair process / in queue
824032 | MS6001FA STAGE 2 SHROUD BLOCK | IIR received - released to repair process / in queue
824033 | MS6001FA STAGE 3 SHROUD BLOCK | IIR received - released to repair process / in queue

## 18.7.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date | Status
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-07-16 | 2025-07-30 | 2025-08-15 | TBA | TBA | TBA | 2025-10-25 | performed strip coating - done next process : Gritblast, Heat tint
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-07-15 | 2025-07-17 | 2025-08-15 | TBA | TBA | TBA | 2025-09-26 | performed FPI - done next process : visual inspection, defect map, CMM dimension measurement
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-07-14 | 2025-08-08 | TBA | TBA | TBA | 2025-08-27 | performed FPI - done next process : visual inspection, defect map, CMM dimension measurement
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25 | incoming inspection - done gathering all data to prepare incoming report - in queue
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | TBA | TBA | TBA | 2025-09-27 | incoming inspection - done gathering all data to prepare incoming report - in queue
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25 | incoming inspection - done gathering all data to prepare incoming report - in queue
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-25 | TBA | TBA | TBA | 2025-08-27 | incoming inspection - done gathering all data to prepare incoming report - in queue
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-25 | TBA | TBA | TBA | 2025-09-27 | incoming inspection - done gathering all data to prepare incoming report - in queue
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-29 | TBA | TBA | TBA | 2025-09-27 | incoming inspection - done gathering all data to prepare incoming report - in queue

## Photo 18.7.25
EETH WO# | Part description | Status | Photo1 | Photo2
824025 | MS6001FA STAGE 1 BLADE | performed strip coating - done next process : Gritblast, Heat tint
824026 | MS6001FA STAGE 2 BLADE | performed FPI - done next process : visual inspection, defect map, CMM dimension measurement
824027 | MS6001FA STAGE 3 BLADE | performed FPI - done next process : visual inspection, defect map, CMM dimension measurement
824028 | MS6001FA STAGE 1 NOZZLE | incoming inspection - done gathering all data to prepare incoming report - in queue
824029 | MS6001FA STAGE 2 NOZZLE | incoming inspection - done gathering all data to prepare incoming report - in queue
824030 | MS6001FA STAGE 3 NOZZLE | incoming inspection - done gathering all data to prepare incoming report - in queue
824031 | MS6001FA STAGE 1 SHROUD BLOCK | incoming inspection - done gathering all data to prepare incoming report - in queue
824032 | MS6001FA STAGE 2 SHROUD BLOCK | incoming inspection - done gathering all data to prepare incoming report - in queue
824033 | MS6001FA STAGE 3 SHROUD BLOCK | incoming inspection - done gathering all data to prepare incoming report - in queue

## 11.7.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-08-12 | 2025-08-17 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-08-14 | 2025-08-19 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-08-07 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-29 | TBA | TBA | TBA | 2025-10-25
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-29 | TBA | TBA | TBA | 2025-10-25
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-29 | TBA | TBA | TBA | 2025-10-25

## Photo 11.7.25
EETH WO# | Part description | Status | Photo1 | Photo2
824025 | MS6001FA STAGE 1 BLADE | performed smoke test next process : strip coating
824026 | MS6001FA STAGE 2 BLADE | perform gritblast cleaning, thisckness measurement next process : strip coating
824027 | MS6001FA STAGE 3 BLADE | performed solution heat treat next process : FPI
824028 | MS6001FA STAGE 1 NOZZLE | next process : FPI, visual inspection
824029 | MS6001FA STAGE 2 NOZZLE | incoming inspection done waiting Incoming report
824030 | MS6001FA STAGE 3 NOZZLE | incoming inspection done waiting Incoming report
824031 | MS6001FA STAGE 1 SHROUD BLOCK | incoming inspection done waiting Incoming report
824032 | MS6001FA STAGE 2 SHROUD BLOCK | in process of Engineering review
824033 | MS6001FA STAGE 3 SHROUD BLOCK | in process of Engineering review

## 3.7.25
EthosEnergy (Thailand) Ltd. Customer Repair Schedule
Order Details | [5 empty] | INCOMING INSPECTION |  |  |  | REPAIR PROCESS |  |  | Plan completion Date
EE TH Order No. | Cust. Name | Power Plant Name | Cust. PO No. | Part Description | Total Qty. rec. | Part Receipt Date | Grit blast& Cleaning & Stripping | Pre Weld Solution Heat Treatment | Incoming Inspection Report | Plan start Weld & Blending Repair | Coating | Final inspection
824025 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 BLADE | 92 | 2025-06-23 | 2025-08-12 | 2025-08-17 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824026 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 BLADE | 92 | 2025-06-23 | 2025-08-14 | 2025-08-19 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824027 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 BLADE | 92 | 2025-06-23 | N/A | 2025-08-07 | 2025-08-29 | TBA | TBA | TBA | 2025-10-25
824028 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 NOZZLE | 24 | 2025-06-23 | 2025-07-08 | 2025-07-14 | 2025-07-29 | TBA | TBA | TBA | 2025-10-25
824029 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 NOZZLE | 24 | 2025-06-23 | 2025-07-04 | 2025-07-10 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824030 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 NOZZLE | 20 | 2025-06-23 | 2025-07-06 | 2025-07-12 | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824031 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 1 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-25 | TBA | TBA | TBA | 2025-10-25
824032 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 2 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-29 | TBA | TBA | TBA | 2025-10-25
824033 | UNEW, Inc | Nghi Son Refinery | PO04102025-HGP | MS6001FA STAGE 3 SHROUD BLOCK | 24 | 2025-06-23 | N/A | N/A | 2025-07-29 | TBA | TBA | TBA | 2025-10-25